## Gantt Chart Template
GANTT CHART | [28 empty] | https://goo.gl/PlIwL0
| PROJECT TITLE | Sickle Cell Anemia: A Bioinformatics study | [5 empty] | COMPANY NAME | [8 empty] | IB UPC
| PROJECT MEMBERS | Uma Sató, Martina Sarrias, Maria Dolça Viella, Julissa Espejo, Sara Delcazo | [5 empty] | DATE | [8 empty] | 2026-05-10
[8 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | Estimated | REAL START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | Start Date |  |  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | WP1: Project Setup & managment |  | 2026-09-24 | 2026-10-01 | 2026-10-28
1.1 | Git Hub Repository Setup & Structuring | Martina S | 2026-09-21 | 2026-10-01 | 2026-10-06 | 5 | 100% | bar: WEEK 1 F to WEEK 2 F
1.2 | Initial Gantt Chart creation | Martina S & Sara D | 2026-09-21 | 2026-10-05 | 2026-10-05 | 0 | 100%
1.3 | Live Project Status Tracking | Martina S & Maria Dolça | 2026-09-21 | 2026-10-05 | 2026-10-28 | 23 | 16% | bar: WEEK 2 M to WEEK 3 W
2 | WP2: Molecular Cause & Healthy State |  | 2026-09-28 | 2026-10-07 | 2026-10-15
2.1 | Gene/protein Identification & Databases | Sara D | 2026-10-07 | 2026-10-07 | 2026-10-10 | 3 | 16% | bar: WEEK 4 M to WEEK 4 R
2.2 | Reference (Healthy) Gene and Protein Sequence Analysis | Sara D | 2026-10-09 | 2026-10-09 | 2026-10-13 | 4 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3. | Initial Structure Retrieval & Gene Context | Sara D | 2026-10-11 | 2026-10-11 | 2026-10-15 | 4 | 16%
2.4. | 3D Structural Analysis of reference protein | Julissa | 2026-10-11 | 2026-10-11 | 2026-10-15 | 4 | 0%
3 | WP3: Disease State & Functional Impact |  | 2026-10-12 | 2026-10-12 | 2026-10-20
3.1 | Pathogenic Variant/Mutation Mapping | Julissa | 2026-10-12 | 2026-10-12 | 2026-10-16 | 4 | 0%
3.2 | Sequence & Structural Comparison (Healthy vs. Disease) | Julissa | 2026-10-14 | 2026-10-14 | 2026-10-18 | 4 | 0%
3.3. | Physiological Impact & Patient Functional Analysis | Maria Dolça | 2026-10-16 | 2026-10-16 | 2026-10-20 | 4 | 0%
4 | WP4: Interspecies Comparative Genomics |  | 2026-10-07 | 2026-10-14
4.1. | Sequence Retrieval for Human + 2 Species | Uma S | 2026-10-14 | 2026-10-14 | 2026-10-17 | 3 | 0%
4.2. | Multiple Sequence Alignment (MSA) & Conservation Analysis | Uma S | 2026-10-17 | 2026-10-17 | 2026-10-20 | 3 | 0%
4.3. | Evolutionary & Biological Implications Synthesis | Uma S | 2026-10-19 | 2026-10-19 | 2026-10-22 | 3 | 0%
5 | WP5: BMC Manuscript Writing & Final Delivery |  | 2026-10-18 | 2026-10-18 | 2026-10-28
5.1. | Main Report Drafting (.md in BMC Format) | Maria Dolça | 2026-10-18 | 2026-10-18 | 2026-10-25 | 7 | 0%
5.2. | References PDF Compilation (references/ folder) | All | 2026-10-20 | 2026-10-20 | 2026-10-26 | 6 | 0%
5.3. | Final Commit, Review & Submission Deadline | All | 2026-10-26 | 2026-10-26 | 2026-10-28 | 2 | 0%
What is the cause of the disease from the gene, protein, structure and function perspectives? ● What are the differences at gene, protein, structure and function levels between a reference/healthy state and the disease-associated state? ● From a biological perspective, how are the differences between reference/healthy state and disease-state impacting the patient’s function? ● What are the differences of the gene, protein, structure and function between humans and at least 2 other relevant species? What biological implications does this have?